## Summary
A2A-CRM - Phase 1 Sprint 1 - Lead Capture Tracker
METRIC | VALUE | NOTES
Total Req IDs | 20 | CRM-LC-001 to CRM-LC-020
Must Have | 13 | Non-negotiable for Sprint 1
Should Have | 7 | Deliver in Phase 2 if Sprint 1 capacity allows
Not Started | 20 | Update as work progresses
In Progress | 0
Complete | 0
Blocked | 0
IMPLEMENTATION ORDER | GROUP | REQ IDS
Group A - Foundation (START HERE) | 3 | LC-011, LC-014, LC-018
Group B - Web Forms | 4 | LC-001, LC-002, LC-015, LC-009
Group C - Imports | 4 | LC-012, LC-003, LC-004, LC-008
Group D - Dedup and Merge | 2 | LC-019, LC-020
Group E - Channel Webhooks | 2 | LC-007, LC-010
Group F - Analytics Ext (Should Have) | 2 | LC-016, LC-017
Group G - UI Should Have | 3 | LC-005, LC-006, LC-013
FOUNDATION FILES (Group A builds once, all groups reuse)
Migration | leads table + lead_programme_interests | database/migrations/
Enums | LeadStatus, LeadTemperature, LeadSource | app/Enums/CRM/
Model | Lead.php | HasUuids + SoftDeletes + InstitutionScope + AuditObserver
Repository | LeadRepository + Interface | app/Repositories/CRM/Lead/
Service | LeadService | app/Services/CRM/Lead/
Events | LeadCreatedEvent, LeadStatusChangedEvent, LeadDuplicateDetectedEvent | app/Events/CRM/
Jobs | DetectLeadDuplicatesJob, RecalculateLeadScoreJob | queue: default
HTTP | StoreLeadRequest, LeadResource, LeadController | app/Http/...
Frontend | index, create, show Blade views + Livewire LeadTable | resources/views/crm/leads/

## LeadCapture Sprint1
A2A-CRM ¦ Phase 1 Sprint 1 ¦ Lead Capture + Source Mgmt ¦ CRM-LC-001 to CRM-LC-020
BRD: MEETCS-BRD-CRM-001 v1.0 ¦ Prepared: April 2026 ¦ Stack: Laravel 13 / PHP 8.3 / Blade / Livewire v4 / Tailwind v4
Req ID | Requirement | Priority | Status | Group / Sprint | Key Files to Create | Dependencies | Completed Date
CRM-LC-011 | Manual lead creation via desktop and mobile (counsellors) | Must Have | Not Started | Group A - Foundation | Lead migration, Lead model, LeadStatus/Temperature/Source enums, LeadRepository, LeadService, StoreLeadRequest, LeadResource, LeadController, API routes, web routes, Blade views index/create/show, Livewire LeadTable | Phase 0 complete
CRM-LC-014 | Mandatory Source field on every lead (google_ads, facebook, walk_in, referral, education_portal, whatsapp, ivr, event, website_organic, csv, api, qr_code) | Must Have | Not Started | Group A - Foundation | LeadSource enum, leads.source column in migration | CRM-LC-011
CRM-LC-018 | Auto-detect duplicate leads on mobile number, email or name+course. Flag or auto-merge per configured rules. | Must Have | Not Started | Group A - Foundation | DetectLeadDuplicatesJob, LeadDuplicateDetectedEvent, LeadService::detectDuplicates() | CRM-LC-011
CRM-LC-001 | Embeddable customisable web enquiry forms (iFrame and native) for institution websites | Must Have | Not Started | Group B - Web Forms | EnquiryForm model+migration, EnquiryFormField model, public form controller, iFrame embed view, public routes (guest) | CRM-LC-011
CRM-LC-002 | Conditional field logic on forms (show/hide fields based on prior answers) | Must Have | Not Started | Group B - Web Forms | EnquiryFormField.conditions JSON column, Alpine.js conditional field rendering | CRM-LC-001
CRM-LC-015 | UTM parameter tracking for all web form and landing page submissions | Must Have | Not Started | Group B - Web Forms | leads.source_utm_params JSON column, UTM extraction in StoreLeadRequest | CRM-LC-001
CRM-LC-009 | QR-code-based lead capture for walk-in enquiries and events | Must Have | Not Started | Group B - Web Forms | QR code generator service, QR download endpoint, source=qr_code auto-set | CRM-LC-001
CRM-LC-012 | Bulk lead upload via Excel/CSV with validation and error report | Must Have | Not Started | Group C - Imports | ImportLeadsJob (queue: bulk-operations), LeadCsvImporter, import validation report Blade view | CRM-LC-011
CRM-LC-003 | Google Ads Lead Form Extensions auto-import via webhook | Must Have | Not Started | Group C - Imports | WebhookController::googleAds(), GoogleAdsWebhookRequest, HMAC signature verification | CRM-LC-011
CRM-LC-004 | Facebook / Instagram Lead Ads auto-import via Meta Lead Ads API | Must Have | Not Started | Group C - Imports | WebhookController::metaLeadAds(), MetaLeadAdsWebhookRequest, Meta verification handshake | CRM-LC-011
CRM-LC-008 | Education portal leads (Shiksha, CollegeDekho, Careers360) importable via API or CSV | Must Have | Not Started | Group C - Imports | PortalLeadImporter, portal adapter classes (Shiksha/CollegeDekho), extends LC-012 base importer | CRM-LC-012
CRM-LC-019 | Manual merge of duplicate lead records with full activity history preserved | Must Have | Not Started | Group D - Dedup | LeadMergeService::merge(), MergeLeadsRequest, merge Alpine.js modal UI, activity_logs migrated to primary | CRM-LC-018
CRM-LC-020 | Flag and link leads matching an existing ERP Student or Alumni record | Must Have | Not Started | Group D - Dedup | ErpStudentLookupService, leads.erp_student_uuid column, DetectLeadDuplicatesJob ERP lookup extension | CRM-LC-018 + ERP API
CRM-LC-007 | WhatsApp Click-to-Chat links auto-create lead record when student initiates conversation | Must Have | Not Started | Group E - Webhooks | WhatsAppWebhookController, inbound BSP payload handler, number extraction, source=whatsapp | CRM-LC-011 + BSP
CRM-LC-010 | Inbound calls to virtual number auto-create lead with caller details and call recording | Must Have | Not Started | Group E - Webhooks | TelephonyWebhookController, CallRecordJob (queue: communications), call_consent_given DPDP enforcement | CRM-LC-011 + IVR
CRM-LC-016 | Multi-touch attribution model (first touch, last touch, linear, configurable) | Should Have | Not Started | Group F - Analytics | lead_touchpoints table+model, AttributionService, attribution_model config per institution | CRM-LC-015
CRM-LC-017 | Cost-per-lead tracking by linking campaign spends to lead source | Should Have | Not Started | Group F - Analytics | campaign_spends table+model, CostPerLeadCalculator service, CPL report on analytics dashboard | CRM-LC-016
CRM-LC-005 | Landing pages built within CRM (drag-and-drop page builder) for lead capture | Should Have | Not Started | Group G - Should Have | LandingPage model+migration, drag-and-drop builder UI (Alpine.js + Livewire), public page renderer | CRM-LC-001
CRM-LC-006 | Live chat widget embedding on institution websites, enquiries create CRM leads | Should Have | Not Started | Group G - Should Have | ChatSession model, Laravel Reverb WebSocket, embeddable chat widget JS, chat-to-lead converter | CRM-LC-001
CRM-LC-013 | Walk-in enquiry registration via kiosk-friendly interface | Should Have | Not Started | Group G - Should Have | Kiosk-mode Blade view (large touch targets), kiosk guard+session, source=walk_in auto-set | CRM-LC-001